## General
Project Title: | On Demand Service
Team Members
Surbhi
Anith
Arun
Farooq
Sibtain
Priority
High
Medium
Low
Status
Planned
Ongoing
Complete

## Objectives
Objectives
# | Name | Release
1 | Design Software Architecture
2 | GUI Design
3 | Database Implementation
4 | User Management (User roles, Registration, Edit, Authentication)
5 | Backend Implementation
6 | Features List
7
8
9
10

## Product Backlog
Project Specificaton | GUI Design
Design Software Architecture | Layout Styling (Bootstrap)
Create Project Structure | View Designing
Requirements Specification | Home Page
Development Environment Setup | Admin Panel
Help/About
Data Access
REST Web Service | Features Implementation
Flask Server
Database Design (MongoDB)
Database Implementation
User Management (User roles, Registration, Edit, Authentication)
Registration
Authenticaton
User Roles
Training

## Release Plan
Release 1 (26.05.2018)
Sprint 1 | 2018-04-14
Sprint 2 | 2018-04-21
Sprint 3 | 2018-04-28
Sprint 4 | 2018-05-05
Sprint 5 | 2018-05-12
Release 2 (06.07.2018)
Sprint 6 | 2018-05-26
Sprint 7 | 2018-06-02
Sprint 8 | 2018-06-09
Sprint 9 | 2018-06-16
Sprint 10 | 2018-06-23
Sprint 11 | 2018-06-30

## Sprint1
Sprint 1
14.04.2018 - 21.04.2018
|  |  |  | Team (Planned) |  |  |  |  | Team (Spent)
Who | Status | Story | Priority
|  |  |  | Surbhi | Anith | Arun | Farooq | Sibtain
| Complete | Feature List Brainstorming |  | 2 | 2 | 2 | 2 | 2
Anith | Complete | Repository Setup (GIT) |  |  | 1
Surbhi | Complete | Requirements Specification |  | 1
Arun | Complete | Project Setup
|  | Development Environment Setup |  | 2 | 2 | 2 | 2 | 2
Team Support Task
|  | REST API | [5 empty] | 1
|  | Planned Total |  | 5 | 5 | 4 | 4 | 5 | 0 | 0 | 0 | 0
|  | Available |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 15
|  | Rest |  | 0 | 0 | 1 | 1 | 0 | 5 | 5 | 5 | 15